Weekly Meeting: Sunday, 04.04.2021

Scrum Master: Hong Hanh Ngo

**1. Check-up**

|  |  |
| --- | --- |
| Sebastian | has done his research about the facts, figures regarding winter sports in mountains   * has the data for winter sport * has to find the explicit data about the traffic   Can try to get interview with the girl, who is doing sky walking. On Monday 05.04 he will have some interviews with the people, who are in clubs. |
| Dominik | Has done one interview with Wolfgang Stöckert.  Has done his research about the effects of pollutions and sent Sebastian. |
| Carlos | Has found websites about the future of winter sports. He will finish it until Monday 05.04. |
| Christina | Has found some sources about the sustainability in skiing resorts and its sustainability goals, which has currently already implemented. She has found different interesting aspect of sustainability (educate, …)  Has done one interview with her friend and plan to make more interviews to a frequent skier. |
| Hanh | Has done her research about the digital and sustainable solutions, which were implemented by other organization. Her research is about the sustainability solutions from ÖSV in World Cup 2015.  Plan to make an interview on Monday 05.04. |

**2. Task for the next week**

- Write the questions for the interview with skiers in the Google Document (**Hanh**)

- Fill out / answer the questions with interview data in the Google Document (deadline Tuesday 06.04 3 p.m)

- Create personas with the information from the Google Document (**Christina**)

- Summarize your research and send the researches to Sebastian (deadline 06.04 8 p.m)

- Write the wiki page (**Sebastian** deadline 07.04 10 a.m)

- Think about the questions for the DSV and fill it in the Google Document (deadline 05.04 8p.m)

- Add the questions for DSV to Sli.do (Hanh deadline 05.04 9 p.m)